## Sheet1
PROJECT BACKLOG
13 | = highest Reference ID number
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 校园动态 | 作为一个大学的一名大学生，我希望知道每天学校发生了哪些有趣的好玩的事情。 | Initial Feature | Not Done | 2 | 98 |  |  | 2
2 | 1 | 1 | user story | 校园新闻 | 作为大学生，我希望及时了解学校的通知、公告 | Initial Feature | Not Done | 1 | 96 |  |  | 1 | 0
3 | 1 | 1 | user story | 校园推文 | 作为大学生，我希望可以更方便的了解社团组织，挖掘自己的兴趣。 | Initial Feature | Not Done | 3 | 95 |  |  | 3
4 | 1 | 1 | user story | 关注 | 作为一个看阅者，希望更多的看到自己喜欢的人、喜欢的社团组织、感兴趣的东西。 | Initial Feature | Not Done | 1 | 93 |  |  | 1 | 0
5 | 1 | 1 | user story | 收藏 | 作为一个看阅者，希望永久保存自己看够值得收藏的东西。 | Initial Feature | Not Done | 1 | 93 |  |  | 2 | 0
6 | 1 | 2 | user story | 转载 | 我希望讲非原创动态转载自己的空间，与他人分享 | Initial Feature | Not Done | 0.5 | 90 |  |  | 1 | 0
7 | 1 | 2 | user story | 点赞 | 我希望为喜欢的作品点赞、支持 | Initial Feature | Not Done | 2 | 90 |  |  | 2 | 0
8 | 1 | 2 | user story | 热事推荐 | 动态的置顶栏，是获赞数最多的作品，不断更新 | Initial Feature | Not Done | 3 | 88 |  |  | 3 | 0
9 | 1 | 2 | user story | 查看活动 | 我希望知道所有的最近的社团、组织活动，增加社交。 | Initial Feature | Not Done | 0.5 | 85 |  |  | 1 | 0
10 | 1 | 2 | user story | 查看校历 | 我想方便的查看校历。 | Initial Feature | Not Done | 2 | 80 |  |  | 2
11 | 1 | 2 | user story | 查看自己的综测记录 | 我希望可以及时方便查看自己的综测成绩记录 | Initial Feature | Not Done | 1 | 70 |  |  | 1 | 0
12 | 1 | 2 | user story | 查看自己的课程表 | 我希望可以及时方便的查看自己的课程表 | Initial Feature | Not Done | 1 | 65 |  |  | 1 | 0
13 | 1 | 2 | user story | 查看自己的学业成绩 | 我希望可以及时方便查看自己的学业成绩 | Initial Feature | Not Done | 1 | 60 |  |  | 1 | 0
14 | 2 | 2 | user story | 查看自己的第二课堂成绩 | 我希望可以及时方便的查看自己的第二课堂成绩 | Initial Feature | Not Done | 3 | 55 |  |  | 3 | 0
15 | 2 | 2 | user story | 求助消息帮助 | 我希望发布买卖二手货、失物招领等求助消息更有效和有方便。 | Initial Feature | Not Done | 1 | 50 |  |  | 1 | 0
16 | 2 | 3 | user story | 宿舍区域打卡 | 作为一个辅导员老师，我向方便的确保学生晚上的安全 | Initial Feature | Not Done | 1 | 45 |  |  | 1 | 0
17 | 2 | 3 | user story | 辅助身份认证 | 作为在校大学生，此APP可以证明自己的学生身份。 | Initial Feature | Not Done | 3 | 43 |  |  | 3
18 | 2 | 3 | user story | 充值饭卡 | 我想随时随地的充值饭卡。 | Initial Feature | Not Done | 1 | 40 |  |  | 1 | 0
19 | 2 | 3 | user story | 饭卡挂失 | 饭卡丢失我想及时挂失饭卡。 | Initial Feature | Not Done | 1 | 33 |  |  | 1
20 | 2 | 3 | user story | 饭卡查询 | 我想随时随地的查询发卡余额 | Initial Feature | Not Done | 2 | 30 |  |  | 2 | 0
Total |  | 20 | [5 empty] | 31
Note on A3: 作者: This is the highest reference ID number used so far.
Note on A4: 作者: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B4: 作者: This is the release where the story will be developped
Note on C4: 作者: This is the sprint where the story will be developped
Note on D4: 作者: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F4: 作者: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G4: 作者: Type of the story.
Note on H4: 作者: Status of the story
Note on I4: 作者: This column is calculated: Ideal Hours * Adjustment Factor
Note on J4: 作者: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L4: 作者: 0 = Lowest Business Value 100 = Highest Business Value
Note on M4: 作者: Enter here the new ideal estimates which are done with planningpoker
Note on N4: 作者: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O4: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P4: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information
Note on C28: 作者: Total amount of stories available in the project backlog
Note on I28: 作者: total amount of estimated hours